# Mentee worksheet

# Negotiate provider contracts

Mentee: Luis Ramirez

Target role: VP Operations

Mentor: Talia Brooks

## Assignment

Luis Ramirez is assigned to lead a scoped provider contract negotiation as a development project for the VP Operations role, with Talia Brooks serving as mentor and guardrail. Luis should create and execute a negotiation plan, align internal stakeholders, engage provider counterparties, manage risks and trade-offs, and bring the work to a clear outcome or recommendation ready for leadership review. He should not commit to terms or positions beyond his authority.

## First steps

☐	Schedule a kickoff with Talia Brooks before engaging the provider.

☐	Use the kickoff to define the scope of the provider contract negotiation, clarify decision rights, identify required approvals, and agree on the check-in cadence.

☐	Clarify the negotiation objective, boundaries, approval requirements, and escalation triggers.

☐	Draft a negotiation plan that includes desired outcomes, acceptable trade-offs, risks, fallback positions, stakeholder messaging, and open questions.

☐	Review the negotiation plan with Talia before any substantive provider discussions.

☐	Identify and align internal stakeholders before presenting positions to the provider.

## Weekly checkpoints

☐	Review progress against the negotiation objective and confirm whether the scope or assumptions have changed.

☐	Discuss stakeholder alignment, including who is supportive, who has concerns, and what decisions are still unresolved.

☐	Review provider discussion notes, including commitments, open issues, risks, and relationship considerations.

☐	Pressure-test financial, operational, and relationship trade-offs before taking new positions.

☐	Confirm whether any issue requires escalation, leadership input, or formal approval.

☐	Assess whether Luis is staying within agreed decision rights and not committing beyond his authority.

☐	Identify the next week’s negotiation priorities and the specific support needed from Talia.

## Report-back prompts

☐	Bring the current negotiation plan and any updates made since the last check-in.

☐	Summarize provider discussions, including key points raised, areas of agreement, areas of disagreement, and open decisions.

☐	Identify the most important risks, trade-offs, and fallback positions currently in play.

☐	Explain how internal stakeholders have been aligned and where alignment remains difficult.

☐	State any recommendation, decision, escalation, or approval needed from leadership.

☐	Describe where mentor input is needed to pressure-test assumptions, improve messaging, or manage risk.

☐	Prepare a final recommendation that is clear, defensible, and ready for leadership review.

## Reflection questions

- What did I learn about leading a provider negotiation at an executive level?

- Where did I create alignment effectively, and where did alignment become difficult?

- How well did I balance operational needs, relationship considerations, and negotiation discipline?

- What assumptions did I make that needed to be tested?

- When did I need mentor support, and what does that reveal about my readiness for a VP Operations role?

- What would I do differently in the next provider contract negotiation?

## Mentee report-back notes

Add notes about what you completed, learned, and need from your mentor next.